## System Test Plan
Section | Planning Item | Details / Guidance | Status | Owner / Notes
Document Info | Project | Day 7 — System and Integration Testing | Planned
Document Info | Version | 1.0 | Planned
Objectives | System behavior | Validate complete application against requirements | Planned
Scope | Functional workflows | Authentication, core journeys, forms, search, checkout/transactions where supported | Planned
Scope | Non-functional checks | Usability and compatibility; performance/security only with suitable authorization and tools | Planned
Applications | E-commerce | Automation Exercise — record exact URL before execution | Not Executed
Applications | Banking | ParaBank — demo accounts and non-real funds only | Not Executed
Applications | Booking | Record exact selected booking demo URL | Not Executed
Environment | Browser and OS | Record browser/version, operating system, date/time, tester, and build/version if available | Pending
Test Data | Synthetic data | Use valid, invalid, missing, malformed, and boundary values; no real sensitive data | Pending
Entry Criteria | Environment available | Authorized environment accessible and sufficiently stable | Pending
Entry Criteria | Cases and data ready | Scope reviewed; test data and expected results identified | Pending
Exit Criteria | Execution status | All in-scope cases have a recorded status or explicit reason for not running | Pending
Exit Criteria | Risks and defects | Open high-severity defects, evidence, and residual risks documented | Pending
Risk | Demo site unavailable | Record date/time; retry; mark Blocked if execution cannot proceed | Open
Risk | Requirements unclear | Document assumptions and clarify expected behavior | Open
Risk | Simulated data confused with actual | Label simulated data and replace with observed results | Open
Deliverable | System Test Plan | Matching Markdown, Word, and Excel plan | Created
Deliverable | Execution Report | Record actual outcomes, evidence, defects, and limitations | Pending